## Sheet1
ID | Phase/Key Milestone | Duration | Week _01 | Week _02 | Week _03 | Week _04 | Week _05 | Week _06 | Week _07 | Week _08 | Week _09 | Week _10 | Week _11 | Week _12 | Week _13 | Week _14 | Week _15 | Week _16 | Week _17
1 | Contact Management: Sales representatives can manage customer contacts easily. | 20 days
2 | Sales Opportunity Tracking: Users can track sales opportunities and update their status. | 10 days
3 | Reporting and Analytics: Sales managers can gain insights into team performance and customer interactions. | 30 days
4 | Integration and Automation: CRM integrated with Outlook email & calendar, sales staff receive automated reminders about meetings and tasks | 20 days
5 | Project Closure | 1 day
| Total | 81 days